## Sheet1
Student can scan a QR Code to register for class | Fix multiple scan issue | Andrew, Matt, Lewis D | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1
| Remove QR code when class finishes | Andrew, Matt, Lewis D | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Haptic feedback on scan | Lewis B, Artur | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Display current class on scan | Andrew, Matt, Lewis B, Artur, Ryan | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1
| Return to main menu after scan | Andrew, Matt | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Staff home page | Display list of all modules for that day | Andrew, Matt, Lewis B, Artur, Ryan | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Highlight current class | Andrew, Matt, Lewis B, Artur | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Modules display based on staff access level | Andrew, Matt, Lewis B, Artur, Ryan | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| QR generated automatically from selecting a class | Andrew, Matt, Lewis B, Artur | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
JUnit Testing - designing and implementing | Module Display | Lewis D, Tristan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Adding Student | Lewis D, Tristan | 3.5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Attendance Overview | Lewis D, Tristan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| QR Data Return | Lewis D, Tristan | 3.5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Database Connection | Lewis D, Tristan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| View Attendance List | Lewis D, Tristan | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Lecture Details | Lewis B, Artur | 2.5 | 2.5 | 2.5 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
| Module Details | Lewis B, Artur | 3 | 3 | 3 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Module List | Lewis B, Artur | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Homepage/Menu | Lewis B, Artur | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| QR Code Display | Lewis B, Artur | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Attendance List | Lewis B, Artur | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
Attendance | Manually add student to class | Andrew, Matt | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1
| View attendance lists of every class | Andrew, Matt, Lewis B, Artur | 5 | 5 | 5 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0
| View attendance data visualisation | Andrew, Matt, Lewis B, Artur | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| Add stored procedures for attendance | Ryan / Lewis | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Database | Add Booking Data | Lewis D, Tristan | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Add Stored Procedure | Lewis D | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Effort remaining | 72.75 | 71.75 | 65.75 | 59.25 | 51 | 48 | 42 | 42 | 42 | 42 | 42
|  | Not started | In progress | Completed